## Slide 1
INS3044 · IT Project Management
Task & Project
Management System
An unhurried 14-week build
PM · Leader
Nguyễn Long Đức
23070435
Developer
Phạm Hồ Bảo
23070455
UI / UX Designer
Kiều Bá Thịnh
23070247
Quality Assurance
Đỗ Huy Hiếu
23070325
Instructors: Dr Nguyễn Phương Anh · MS Đỗ Tiến Thành
Faculty of Applied Sciences · VNU · June 2026
Notes: Welcome everyone. Group 14 consists of four members: Đức as project manager, Bảo on development, Thịnh handling UI and UX, and Hiếu leading QA. We've spent 14 weeks building a web-based Task and Project Management System from scratch, applying every major discipline of IT project management along the way. The tagline 'an unhurried 14-week build' captures our approach: we prioritised sound process over speed, which is exactly what INS3044 asks us to demonstrate. The talk is structured across eight sections — WBS, PERT, CPM, budgeting, risk, communication, EVM monitoring, and the prototype demo. Questions are welcome throughout.

## Slide 2
OVERVIEW
Agenda
Eight sections, one project
Group 14 · INS3044 · June 2026
1 / 24
§ I
Scope & Objectives
CLO 1, 2
§ II
Work Breakdown Structure
CLO 2, 5
§ III
Timeline & Milestones
CLO 2, 4, 5
§ IV
Resource Management
CLO 2, 8, 9
§ V
Risk Management
CLO 3, 6
§ VI
Communication
CLO 4, 5, 8, 9, 12
§ VII
Monitoring & EVM
CLO 7
§ VIII
Prototype & Lessons
CLO 7, 8, 9
Notes: Our presentation is organised into eight sections, mirroring the structure of a full project management cycle. We'll open with scope and objectives, move through the planning artefacts — WBS, schedule, budget — then the execution controls of risk and communication, finish with EVM monitoring and the live demo. Each section maps to specific CLOs in the INS3044 syllabus.

## Slide 3
§
I
Scope & Objectives
CLO 1, 2 · Ch. 1, 2, 3
Group 14 · INS3044 · June 2026
Notes: Section I sets the foundation. We'll cover the business context, define what's in scope and what's explicitly out of scope, and walk through our five SMART objectives that tie directly to the INS3044 CLOs.

## Slide 4
SCOPE & OBJECTIVES
Project at a Glance
Group 14 · INS3044 · June 2026
2 / 24
33,600,000 VND
Budget at Completion (BAC)
43 working days
Critical Path Duration
3,080,000 VND
Total Risk EMV (Cost)
5 core features
Prototype Feature Areas
BAC breakdown: Labour 24M · OH 20% · G&A reallocated · Contingency 2.4M · Mgmt reserve 0.68M
Risk EMV coverage: Contingency 2,400,000 + Management reserve 680,000 = 3,080,000 VND ✓
Team: Nguyễn Long Đức (23070435, PM) · Phạm Hồ Bảo (23070455, Dev) · Kiều Bá Thịnh (23070247, UI/UX) · Đỗ Huy Hiếu (23070325, QA)
Notes: These four KPIs define the project baseline. Budget at Completion is 33.6 million VND, covering labour, overhead, G&A, contingency, and management reserve. The critical path is 43 working days — we'll see how we derived that in Section III. The risk EMV of 3.08 million VND is fully covered by contingency plus a management reserve top-up. And we have five prototype features to deliver.

## Slide 5
SCOPE & OBJECTIVES
Scope Boundaries
Group 14 · INS3044 · June 2026
3 / 24
IN SCOPE
· Project CRUD (create, read, update, delete)
· Task CRUD with user assignment
· Status workflow: To Do → In Progress → Done
· Task deadline with overdue highlighting
· Task progress % (0–100%) per task
· Project dashboard (counts & progress)
· Role-based UI: Admin / PM / Member
· Responsive single-page web application
· Functional prototype (≥ 3 features live)
· Full PM documentation (WBS, CPM, budget, risk, EVM)
OUT OF SCOPE
✗ Native iOS / Android application
✗ Real-time chat or messaging
✗ Billing, invoicing, payment processing
✗ Third-party integrations (Slack, GitHub, Outlook)
✗ Multi-tenancy (multiple organisations)
✗ Post-launch maintenance or support
✗ Automated email / push notifications
Notes: The left column shows what's explicitly in scope — agreed by all four team members and traceable to the project registration. The right column documents what we deliberately excluded and why. This scope lock is our first line of defence against scope creep, which is Risk R2 in our risk register.

## Slide 6
SCOPE & OBJECTIVES
SMART Objectives
Group 14 · INS3044 · June 2026
4 / 24
# | Objective | CLO
OBJ-1 | Deliver working prototype: task CRUD, assignment, deadline tracking, progress monitoring for 3 roles — demo at W10, submit at W14 | CLO 1, 2
OBJ-2 | Complete all 16 WBS Level 3 packages within 480 person-hours (±10%) by Week 14; tracked weekly in Trello | CLO 2, 4
OBJ-3 | Pass UAT with ≥ 80% test coverage and ≤ 10 defects/KLOC; UAT sign-off at Week 12 | CLO 3, 6
OBJ-4 | Identify ≥ 6 risks; maintain contingency reserve ≥ Total Risk EMV; risk register updated bi-weekly | CLO 3, 6
OBJ-5 | Submit full ZIP package (report, prototype, PPTX+PDF, evidence) before Week 14 deadline | CLO 7, 8, 9
Notes: Each of our five objectives is Specific, Measurable, Achievable, Relevant, and Time-bound — the SMART framework. OBJ-1 covers the prototype deliverables. OBJ-2 covers our 480-hour budget. OBJ-3 covers quality at UAT. OBJ-4 covers risk management and the EMV-driven contingency. OBJ-5 covers the final submission. Every objective is tagged to one or more CLOs, so we can demonstrate coverage.

## Slide 7
§
II
Work Breakdown Structure
CLO 2, 5 · Ch. 4, 5
Group 14 · INS3044 · June 2026
Notes: Section II covers the Work Breakdown Structure. The WBS is our definitive scope baseline — every deliverable maps to exactly one Level 3 work package. We'll look at the three-level hierarchy and the WBS dictionary.

## Slide 8
WORK BREAKDOWN STRUCTURE
WBS — Three-Level Hierarchy
Group 14 · INS3044 · June 2026
5 / 24
1.0
Task & Project Management System
1.1
Project Management
1.1.1
Project Charter & Kickoff
1.1.2
Status Meetings (12 × 2 h)
1.1.3
Risk Reviews
1.1.4
Final Report Writing
1.2
Requirements & Analysis
1.2.1
Stakeholder Interviews
1.2.2
Requirements Document
1.2.3
Requirements Sign-off
1.3
System Design
1.3.1
UI/UX Design (Figma)
1.3.2
Database / Data-Model Schema
1.3.3
API / Service Contract
1.4
Development
1.4.1
Frontend (React + Vite + TS)
1.4.2
Backend / Persistence Layer
1.4.3
Integration & Wiring
1.5
Testing & QA
1.5.1
Unit Tests (Vitest)
1.5.2
Integration Tests
1.5.3
User Acceptance Test
1.6
Documentation
1.6.1
User Guide
1.6.2
Technical Documentation
1.7
Presentation & Submission
1.7.1
Slide Deck
1.7.2
Rehearsal
WBS Level 3 Hours Summary
1.1 PM
60 h
1.2 Req
50 h
1.3 Design
80 h
1.4 Dev
180 h
1.5 QA
60 h
1.6 Docs
30 h
1.7 Pres
20 h
Total Labor: 480 hours × 50,000 VND/h = 24,000,000 VND
→ See Budget Rollup in Section IV
Notes: The WBS decomposes the project into manageable chunks. Level 1 is the project itself. Level 2 has seven branches — Project Management, Requirements, Design, Development, QA, Documentation, and Presentation. Level 3 gives us 16 work packages that together account for 100% of the scope — verified against the scope statement. Total estimated effort is 480 person-hours.

## Slide 9
§
III
Timeline & Milestones
CLO 2, 4, 5 · Ch. 4, 8, 10
Group 14 · INS3044 · June 2026
Notes: Section III is the schedule heart of the project. We'll cover PERT three-point estimation for six activities, the full CPM forward and backward pass, and the critical path identification. The Gantt overview shows all 16 work packages mapped against the project timeline with six key milestones.

## Slide 10
TIMELINE & MILESTONES
Gantt Chart — 14-Week Timeline
Group 14 · INS3044 · June 2026
6 / 24
WBS
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
1.1.1
Charter & Kickoff
Đức
1.1.2
Status Meetings
Đức
1.1.3
Risk Reviews
Đức
1.2.1
Stakeholder Interv
Đức
1.2.2
Requirements Doc
Bảo
1.2.3
Req Sign-off
Đức
1.3.1
UI/UX Design
Thịnh
1.3.2
DB Schema
Bảo
1.3.3
API Contract
Bảo
1.4.1
Frontend Dev
Bảo+Thịnh
1.4.2
Backend Dev
Bảo
1.4.3
Integration
Bảo
1.5.1
Unit Tests
Hiếu
1.5.2
Integration Tests
Hiếu
1.5.3
UAT
Hiếu
1.6.1
User Guide
Thịnh
1.6.2
Tech Docs
Bảo
1.7.1
Slide Deck
Thịnh
1.7.2
Rehearsal
Đức
M1: Charter Approved
M2: Req Sign-off
M3: Design Review
M4: Proto Demo
M5: Testing Complete
M6: Final Submission
Critical path
Non-critical
Notes: The Gantt chart shows all 16 Level 3 work packages across the 14-week project. The critical path activities are highlighted in burnt sienna — they have zero float and any delay on them directly delays the project end. The non-critical activities are in muted brown. Six diamond milestones mark key delivery points. Activity F (Backend Development) has 8 days of float — it can slip without affecting the critical path.

## Slide 11
TIMELINE & MILESTONES
PERT Three-Point Estimates
Group 14 · INS3044 · June 2026
7 / 24
Activity | Description | O (d) | M (d) | P (d) | TE = (O+4M+P)/6 | σ = (P−O)/6 | Notes
A | Requirements | 3 | 5 | 9 | 5.33 d | 1.00 d | Critical path
B | UI/UX Design | 5 | 10 | 18 | 10.50 d | 2.17 d | Critical path
E | Frontend Dev | 10 | 15 | 22 | 15.33 d | 2.00 d | Critical path
G | Integration | 3 | 5 | 8 | 5.17 d | 0.83 d | Critical path
H | Testing | 5 | 8 | 14 | 8.50 d | 1.50 d | Critical path
F | Backend Dev | 8 | 12 | 20 | 12.67 d | 2.00 d | Non-critical; 8 d float
Worked Example — Activity B (UI/UX Design)
O = 5 days, M = 10 days, P = 18 days TE = (5 + 4×10 + 18) / 6 = 63 / 6 = 10.5 days σ = (18 − 5) / 6 = 13 / 6 ≈ 2.17 days Interpretation: ~68% probability of completing within 10.5 ± 2.17 days.
Notes: PERT uses three-point estimation to account for uncertainty. For each activity we record an Optimistic (O), Most Likely (M), and Pessimistic (P) duration. The weighted expected time TE = (O + 4M + P) / 6 gives more weight to the most likely estimate. Standard deviation σ = (P − O) / 6 tells us how certain we are. Activity B — UI/UX Design — is the work-through example shown here.

## Slide 12
TIMELINE & MILESTONES
CPM — Forward & Backward Pass
Group 14 · INS3044 · June 2026
8 / 24
Act. | Desc. | Dur. | Predecessors | ES | EF | LS | LF | Slack | CP?
A | Requirements | 5 d | — | 0 | 5 | 0 | 5 | 0 | ★
B | UI/UX Design | 10 d | A | 5 | 15 | 5 | 15 | 0 | ★
C | DB Schema | 4 d | A | 5 | 9 | 14 | 18 | 9 | 
D | API Design | 5 d | A | 5 | 10 | 13 | 18 | 8 | 
E | Frontend Dev | 15 d | B | 15 | 30 | 15 | 30 | 0 | ★
F | Backend Dev | 12 d | C, D | 10 | 22 | 18 | 30 | 8 | 
G | Integration | 5 d | E, F | 30 | 35 | 30 | 35 | 0 | ★
H | Testing | 8 d | G | 35 | 43 | 35 | 43 | 0 | ★
Notes: The Critical Path Method gives us the longest sequence of dependent activities and the float available on non-critical ones. Forward pass: ES = max(EF of predecessors), EF = ES + duration. Backward pass: LF = min(LS of successors), LS = LF − duration. Slack = LS − ES. Critical activities have zero slack. Activity F has 8 days of float — it can slip by a week before affecting the project end date.

## Slide 13
TIMELINE & MILESTONES
The Critical Path
Group 14 · INS3044 · June 2026
9 / 24
A
Requirements 5 days
→
B
UI/UX Design 10 days
→
E
Frontend Dev 15 days
→
G
Integration 5 days
→
H
Testing 8 days
A → B → E → G → H = 5 + 10 + 15 + 5 + 8 = 43 working days
≈ 9 calendar weeks · Activity F (Backend Dev) has 8 days of float
Activity | Slack | Interpretation
F — Backend Dev | 8 days | Can slip up to 8 days without delaying project
D — API Design | 8 days | Can slip up to 8 days
C — DB Schema | 9 days | Can slip up to 9 days
Notes: The critical path is the sequence of activities with zero float — any delay on them directly delays the project. It runs A → B → E → G → H, totalling 43 working days or approximately 9 calendar weeks. Activity F — Backend Development — has 8 days of float, giving us a scheduling buffer. The project duration is dominated by the Frontend Development activity at 15 days.

## Slide 14
§
IV
Resource Management
CLO 2, 8, 9 · Ch. 5, 11, 12
Group 14 · INS3044 · June 2026
Notes: Section IV covers how we allocate people, budget, and materials to the project. The RACI matrix defines who does what across all 10 major work packages. The bottom-up budget rolls up from Level 3 hours to a total BAC of 33.6 million VND.

## Slide 15
RESOURCE MANAGEMENT
RACI Matrix — Responsibility Assignment
Group 14 · INS3044 · June 2026
10 / 24
Work Package | WBS | Đức (PM) | Bảo (Dev) | Thịnh (UI/UX) | Hiếu (QA)
Project Planning | 1.1.1 | A | C | I | I
Requirements | 1.2 | A | R | R | C
UI/UX Design | 1.3.1 | I | C | A/R | I
DB Schema | 1.3.2 | A | R | I | C
API Design | 1.3.3 | A | R | I | I
Frontend Dev | 1.4.1 | C | C | A/R | I
Backend Dev | 1.4.2 | I | A/R | I | C
Unit Testing | 1.5.1 | I | C | I | A/R
Documentation | 1.6 | C | C | C | A/R
Presentation | 1.7 | A | R | R | R
R = Responsible · A = Accountable · C = Consulted · I = Informed
Notes: The RACI matrix answers: who is Accountable, Responsible, Consulted, and Informed for each work package. Key verification rules from Chapter 12: exactly one Accountable per row, at least one Responsible per row, and no team member is purely Informed. Each of our four members carries a mix of A and R roles — no one is just a passive recipient of information.

## Slide 16
RESOURCE MANAGEMENT
Bottom-Up Budget Rollup
Group 14 · INS3044 · June 2026
11 / 24
WBS | Work Package | Hours | Cost (VND)
1.1 | Project Management | 60 | 3,000,000
1.2 | Requirements & Analysis | 50 | 2,500,000
1.3 | System Design | 80 | 4,000,000
1.4 | Development | 180 | 9,000,000
1.5 | Testing & QA | 60 | 3,000,000
1.6 | Documentation | 30 | 1,500,000
1.7 | Presentation & Submission | 20 | 1,000,000
LABOR | Subtotal (480 h × 50K) | 480 | 24,000,000
 | + Overhead 20% |  | 4,800,000
 | + G&A 10% (reallocated) |  | 1,720,000
 | + Contingency 10% |  | 2,400,000
 | + Management Reserve |  | 680,000
BAC | Budget at Completion |  | 33,600,000 VND
BAC
33,600,000
VND
480 hours × 50,000/h + overhead + contingency
Notes: The budget is built bottom-up from the WBS. We estimate hours per Level 3 work package, multiply by the blended labor rate of 50,000 VND per hour, then add overhead, G&A, contingency, and management reserve. The labor subtotal of 24 million VND carries a 20% overhead and 10% G&A. The contingency reserve of 2.4 million is the primary risk buffer, topped up by a management reserve of 680,000 drawn from the G&A buffer.

## Slide 17
RESOURCE MANAGEMENT
Time-Phased Budget — Planned Value Curve
Group 14 · INS3044 · June 2026
12 / 24
0%
25%
50%
75%
100%
VND
2,688K
M1
5,040K
M2
8,400K
M3
13,440K
M4
18,480K
M5
23,520K
M6
28,560K
M7
33,600K
M8
Month | PV (VND) | %
M1 | 2,688,000 | 8%
M2 | 5,040,000 | 15%
M3 | 8,400,000 | 25%
M4 | 13,440,000 | 40%
M5 | 18,480,000 | 55%
M6 | 23,520,000 | 70%
M7 | 28,560,000 | 85%
M8 | 33,600,000 | 100%
Notes: The PV curve shows cumulative planned spend across the 8-month project timeline. It's front-loaded — heavy spending in months 4 through 7 during the development phase, lighter in the planning and final submission months. By month 8, the cumulative PV reaches the full BAC of 33.6 million VND. This curve was locked at Week 1 as the cost baseline for EVM tracking.

## Slide 18
§
V
Risk Management
CLO 3, 6 · Ch. 7
Group 14 · INS3044 · June 2026
Notes: Section V documents our risk management process — identification, assessment, EMV calculation, and mitigation planning for six key risks. The total risk EMV of 3.08 million VND drives the contingency reserve. We'll also look at the 3×3 risk heatmap and reconcile EMV against our budgeted contingency.

## Slide 19
RISK MANAGEMENT
Risk Register — 6 Risks with EMV
Group 14 · INS3044 · June 2026
13 / 24
ID | Risk Description | Cat. | L | Cost Impact | Time Impact | EMV Cost | EMV Time | Strategy | Owner
R1 | Member unavailable (illness/conflict) | People | 0.30 | 1,000,000 | 5 d | 300,000 | 1.50 d | Contingency / Accept | Đức
R2 | Scope creep — new requirements added | Scope | 0.50 | 3,000,000 | 10 d | 1,500,000 | 5.00 d | Avoid + Reduce | Đức
R3 | Stack unfamiliarity (React 19, TS) | Tech | 0.40 | 500,000 | 7 d | 200,000 | 2.80 d | Reduce | Bảo
R4 | Data loss / version control failure | Tech | 0.15 | 2,000,000 | 3 d | 300,000 | 0.45 d | Reduce | Thịnh
R5 | FE/BE integration failure at W7 | Tech | 0.35 | 2,000,000 | 8 d | 700,000 | 2.80 d | Reduce | Hiếu
R6 | Meeting coordination issues | People | 0.40 | 200,000 | 2 d | 80,000 | 0.80 d | Accept | Đức
 | TOTAL EMV |  |  |  |  | 3,080,000 VND | 13.35 d |  | 
Notes: We identified six risks through team brainstorming and analogy with prior student projects. Each is scored on likelihood (0–1), with cost and time impacts. EMV = Likelihood × Impact gives us the expected monetary value. R2 — scope creep — has the highest EMV at 1.5 million VND, driving our formal change control process. The total EMV cost of 3.08 million VND and time EMV of 13.35 days are the key inputs to our contingency planning.

## Slide 20
RISK MANAGEMENT
Risk Heatmap — Likelihood × Impact
Group 14 · INS3044 · June 2026
14 / 24
LIKELIHOOD →
IMPACT →
R2
R3
R5
R1
R6
R4
HIGH RISK
MEDIUM
LOW RISK
Risk | L | Impact | Zone
R1 — Member unavailable | 0.30 | 5 d | Medium
R2 — Scope creep | 0.50 | 10 d | High
R3 — Stack unfamiliarity | 0.40 | 7 d | High
R4 — Data loss | 0.15 | 3 d | Low
R5 — Integration failure | 0.35 | 8 d | High
R6 — Meeting issues | 0.40 | 2 d | Medium
Notes: The heatmap plots each risk on a 3×3 grid of Likelihood versus Impact. High-likelihood or high-impact risks land in the red zone at top-right — R2, R3, and R5 require active mitigation. Medium risks R1 and R6 are monitored. R4 is low-likelihood and low-impact, so we accept it with preventive measures in place. The heatmap helps prioritise where to focus contingency effort.

## Slide 21
RISK MANAGEMENT
EMV Reconciliation
Group 14 · INS3044 · June 2026
15 / 24
Item | Amount (VND) | Notes
Total Risk EMV (cost) | 3,080,000 | From risk register Table 14
Contingency reserve (10% of labor) | 2,400,000 | From budget baseline Table 10
Gap (EMV − Contingency) | 680,000 | EMV exceeds contingency
Management reserve (from G&A buffer) | + 680,000 | Drawn from G&A; approved by PM
Adjusted G&A (reduced from 2,400,000) | 1,720,000 | G&A reduced by 680,000
TOTAL RISK COVERAGE | 3,080,000 VND | Full EMV covered ✓
Budget at Completion (unchanged) | 33,600,000 | Total budget unchanged
EMV = Contingency + Mgmt Reserve
3,080,000
VND
= 2,400,000 + 680,000
Notes: Our contingency reserve of 2.4 million VND alone doesn't fully cover the total risk EMV of 3.08 million — there's a gap of 680,000 VND. We address this by reallocating from the G&A buffer, which was originally budgeted at 2.4 million VND. Reducing G&A to 1.72 million closes the gap while maintaining full EMV coverage. This decision was made at the Week 3 risk review and documented in meeting minutes. The total project budget remains 33.6 million VND — the reserves are reallocated, not added.

## Slide 22
§
VI
Communication & Collaboration
CLO 4, 5, 8, 9, 12 · Ch. 9, 11, 12
Group 14 · INS3044 · June 2026
Notes: Section VI covers how the team communicates and resolves conflict. We use a structured 6-step conflict resolution process for interpersonal issues, and a formal change control process for scope changes. We'll also look at the stakeholder power/interest grid and our communication channel matrix.

## Slide 23
COMMUNICATION
Conflict Resolution & Stakeholder Strategy
Group 14 · INS3044 · June 2026
16 / 24
6-Step Conflict Resolution
1
Identify root causes
PM calls private session; each party states position in one sentence
2
Gather facts
Review task logs, commit history, WBS — no hearsay
3
Facilitate open discussion
Moderated by PM; time-boxed to 15 min per issue
4
Focus on issues, not personalities
PM enforces ground rules; redirect from 'you' to 'the decision'
5
Seek win-win resolutions
Explore trade-offs; document rationale
6
Document agreements
Added to meeting minutes within 24 h; all parties confirm via Teams
Stakeholder Power / Interest Grid
 | Low Interest | High Interest
High Power | Monitor (Peer Groups) | Keep Satisfied (Instructor, Univ.)
Low Power | Keep Informed (Bystanders) | Keep Informed (End Users)
Notes: The 6-step conflict resolution process ensures disagreements are handled constructively. Key principles: focus on the issue not the person, document agreements immediately, and escalate only when necessary. The stakeholder power/interest grid maps five stakeholder groups — instructors and the university are high power/high interest and require active engagement. Peer groups and end users need different strategies.

## Slide 24
§
VII
Monitoring & EVM
CLO 7 · Ch. 10
Group 14 · INS3044 · June 2026
Notes: Section VII is the project control heart — Earned Value Management. At Week 6 we took a mid-project snapshot. The results show the project is over budget (CPI = 0.75) and behind schedule (SPI = 0.45). We'll look at the EVM metrics, the corrective action plan, and the issue log.

## Slide 25
MONITORING & EVM
EVM Status — Week 6 Snapshot
Group 14 · INS3044 · June 2026
17 / 24
0.75
Cost Performance Index (CPI)
Over budget
0.45
Schedule Perf. Index (SPI)
Behind schedule
44.8M
Est. at Completion (EAC)
Forecast: 33.6M → 44.8M
−2.5M
Cost Variance (CV)
Over budget by 2.5M
−11.2M
Variance at Completion (VAC)
Forecast overrun
Metric | Formula | Workings | Value
BAC | Budget at Completion | From budget baseline | 33,600,000 VND
PV | Planned Value at W6 | 50% of BAC | 16,800,000 VND
EV | Earned Value | M1+M2+M3+partial = 500K+2.5M+4M+0.5M | 7,500,000 VND
AC | Actual Cost | 200 h × 50,000 VND/h | 10,000,000 VND
CV | Cost Variance | EV − AC = 7.5M − 10M | −2,500,000 VND
SV | Schedule Variance | EV − PV = 7.5M − 16.8M | −9,300,000 VND
CPI | Cost Perf. Index | EV / AC = 7.5M / 10M | 0.75
SPI | Schedule Perf. Index | EV / PV = 7.5M / 16.8M | ≈ 0.45
EAC | Estimate at Completion | BAC / CPI = 33.6M / 0.75 | 44,800,000 VND
ETC | Estimate to Complete | EAC − AC = 44.8M − 10M | 34,800,000 VND
VAC | Variance at Completion | BAC − EAC = 33.6M − 44.8M | −11,200,000 VND
Notes: At the Week 6 milestone checkpoint, we're tracking three metrics. Earned Value of 7.5 million VND comes from completed milestones: Charter (500K), Requirements (2.5M), Design Review (4M), and partial prototype (500K). Actual Cost is 10 million VND from 200 logged hours at 50,000 VND per hour. Planned Value at Week 6 should be 50% of BAC = 16.8 million VND. The variance analysis reveals we're both over budget and behind schedule.

## Slide 26
MONITORING & EVM
Issue Log & Change Control
Group 14 · INS3044 · June 2026
18 / 24
Issue Log
ID | Week | Description | Owner | Status
ISS-001 | W3 | Stakeholder interviews took +3 h | Đức | Closed
ISS-002 | W5 | react-router-dom v7 routing broken | Bảo | Closed
ISS-003 | W6 | M4 Integration milestone at risk | Đức | Open
Change Request CR-001
Field | Value
Date | Week 6
Requester | Bảo
Description | Replace Supabase (cloud) with local state + mock data
Impact — Time | +1 day float recovered; no schedule impact
Impact — Cost | −200,000 VND (eliminates Supabase setup)
Impact — Scope | Removes cloud sync; already in Out-of-Scope
Decision | APPROVED
Status | IMPLEMENTED
Notes: The issue log tracks problems as they arise. ISS-001 was closed — stakeholder interviews ran 3 hours over. ISS-002 was closed — we downgraded react-router-dom from v7 to v6 as a workaround. ISS-003 is open — the Week 10 integration milestone is at risk. The change control table shows CR-001, which approved replacing Supabase with local state to simplify the prototype for the demo. This had a positive schedule impact and minor cost saving.

## Slide 27
§
VIII
Prototype & Lessons
CLO 7, 8, 9 · Ch. 13
Group 14 · INS3044 · June 2026
Notes: Section VIII closes the loop — we show the live demo plan for three prototype features, then reflect on five key lessons learned tagged to their relevant CLOs. We'll also confirm full CLO coverage across all nine learning outcomes.

## Slide 28
PROTOTYPE & LESSONS
Prototype Demonstration Plan
Group 14 · INS3044 · June 2026
19 / 24
Feature 1 · 90 s
Task CRUD + Assignment
Script:
Navigate to /tasks Create task: 'Design landing page', assignee = 'Bảo', deadline = June 20, priority = High → Verify task appears with assignee badge
WBS: WBS 1.4.1
Owner: Bảo + Thịnh
Feature 2 · 60 s
Deadline Management + Overdue Highlight
Script:
Show task with past deadline (yesterday: June 15) → Red overdue badge displayed → Filter by 'Overdue'
WBS: WBS 1.3.1
Owner: Thịnh
Feature 3 · 60 s
Progress Dashboard
Script:
Navigate to /dashboard → Project cards with counts → Task progress bar (e.g., 60%) → Real-time metric aggregation
WBS: WBS 1.4.1, 1.4.2
Owner: Bảo
Demo URL: http://localhost:5173 · Run: npm install && npm run dev
Notes: We demonstrate three core features in under 3 minutes. Feature 1 is Task CRUD with assignment — showing how to create a task, assign it to a team member, set priority and deadline. Feature 2 is deadline management with overdue highlighting — the system automatically flags past-deadline tasks in red. Feature 3 is the progress dashboard — project-level and task-level metrics aggregated in real time. The demo environment is localhost:5173.

## Slide 29
PROTOTYPE & LESSONS
Lessons Learned
Group 14 · INS3044 · June 2026
20 / 24
ID | Lesson | Evidence / Action | CLO Tags
LL-1 | Scope creep at W6 | CR-001 formalised scope lock; 4 h recovered | CLO 3, 9
LL-2 | PERT estimates too optimistic | Activity B took 14 days; TE=10.5. Use 1.2× multiplier. | CLO 2, 5
LL-3 | react-router v7 incompatibility | Downgraded to v6; 3 rollback commits. Pin versions. | CLO 3, 5
LL-4 | EVM was reactive, not proactive | Week 6 VAC = −11.2M. Implement weekly EVM mini-check. | CLO 6, 7
LL-5 | Parallel dev without frozen API contract | 2 days rework at W7 integration. Freeze API at W5. | CLO 2, 4
Notes: Five concrete lessons from the project. LL-1: scope creep consumed 4 hours before CR-001 formalised the scope lock — we now require a change request form from day one. LL-2: PERT estimates were too optimistic — Activity B took 14 days vs. 10.5 estimated. Future projects should use a 1.2× multiplier for design-phase estimates. LL-3: react-router v7 broke our build — we now pin versions in package.json. LL-4: EVM was reactive; we'll implement weekly mini-checks going forward. LL-5: parallel dev without a frozen API contract caused 2 days of rework at integration.

## Slide 30
PROTOTYPE & LESSONS
CLO Coverage Matrix — All 9 CLOs
Group 14 · INS3044 · June 2026
21 / 24
CLO | Description | Section | Evidence
CLO 1 | APPLY PM principles | § 1 | SMART objectives; full PM cycle
CLO 2 | IMPLEMENT scope / HR / time / cost | § 1–4 | WBS, CPM, RACI, bottom-up budget
CLO 3 | IMPLEMENT integration / risk / quality | § 5, § 8 | Risk EMV; quality metrics; CR-001
CLO 4 | IMPLEMENT systems & decisions | § 6, § 8 | Decision process; live demo
CLO 5 | USE tools / processes / techniques | § 2–3 | WBS tool, MS Project, PERT/CPM
CLO 6 | PERFORM risk analysis & contingency | § 5 | 6 risks; EMV; contingency reconciliation
CLO 7 | PERFORM overall evaluation | § 7 | 10 EVM metrics; 5 lessons tagged
CLO 8 | IMPLEMENT overall project plans | All | Report is the project plan; ZIP package
CLO 9 | Autonomy & personal qualities | § 6, § 8 | 4 members with A/R roles; conflict process
Coverage check: All 9 CLOs are demonstrably addressed through specific report sections and evidence. ✓
Notes: Every one of the nine INS3044 Course Learning Outcomes is demonstrably covered in this report. CLO 1 through CLO 9 map to specific sections and evidence artefacts. The coverage check confirms full CLO achievement across scope, time, cost, risk, quality, communication, and project delivery.

## Slide 31
Thank you
Questions & Discussion
Group 14 · INS3044 IT Project Management
PM · Leader
Nguyễn Long Đức
23070435
Developer
Phạm Hồ Bảo
23070455
UI / UX Designer
Kiều Bá Thịnh
23070247
Quality Assurance
Đỗ Huy Hiếu
23070325
Nguyễn Long Đức (23070435) · Phạm Hồ Bảo (23070455) · Kiều Bá Thịnh (23070247) · Đỗ Huy Hiếu (23070325)
Faculty of Applied Sciences · Vietnam National University · June 2026
Notes: Thank you for your attention. We're happy to take questions on any aspect of the project — from the PERT calculations to the EVM corrective action plan. All four team members can answer questions in their respective areas: Đức on schedule and risk, Bảo on technical implementation, Thịnh on design and UX, and Hiếu on testing and quality. The full report, prototype, and presentation materials are available in the submission ZIP.